## Sheet1
User Story | Description | Sprint | Sprint Start | Sprint End | Status | Start Date | End Date | Efforts | Spillover
#505975 | Fit to screen and zoom-in | 2024-07 SPT | 2024-04-04 | 2024-04-17 | Done | 2024-04-10 | 2024-04-16 | 2 | No
#526604 | Create topology toolbar UI component | 2024-08 SPT | 2024-04-18 | 2024-05-01 | Done | 2024-04-08 | 2024-04-22 | 3 | No
#530178 | Belden UI Core Components (Textfield, Divider & Typography) | 2024-09 SPT | 2024-05-02 | 2024-05-15 | Done | 2024-04-25 | 2024-04-30 | 3 | No
#486522 | Context Menu- UI | 2024-10 SPT | 2024-05-16 | 2024-05-29 | Done | 2024-04-24 | 2024-05-30 | 5 | Yes
#531011 | Zoom functionality - Dynamically update zoom level percentage based on yfiles | 2024-10 SPT | 2024-05-16 | 2024-05-29 | Done | 2024-05-16 | 2024-05-21 | 3 | No
#543253 | PR review and Unit test cases Context Menu | 2024-11 SPT | 2024-05-30 | 2024-06-12 | Done | 2024-06-03 | 2024-06-06 | 3 | No
#486538 | background image for canvas | 2024-11 SPT | 2024-05-30 | 2024-06-12 | In Progress | 2024-06-04 | _ | 3 | Yes
#486538 | background image for canvas | 2024-12 SPT
#486519 | Edge labels | 2024-13 SPT
#489972 | Implement Modal dialog for auto update | 2024-14 SPT
#551536 | Delete Edge Labels | 2024-14 SPT
#486528 | Bug Fix | 2024-15 SPT
#552804 | Background Image Fix | 2024-15 SPT
#489992 | Implement: Show the Last check date and time | 2024-15 SPT
#559237 | UTUX: Bug Fix - Issues in Resizing | 2024-15 SPT
#559498 | UTUX:Implement automatic check on application launch | 2024-16 SPT
#559868 | Labels/Text on the Dialogs are not in sync | 2024-16 SPT
#559902 | Symbols for 'Subnet' and 'Template' are incorrect | 2024-16 SPT
#560435 | Device/Endpoint get the same name | 2024-16 SPT
#560447 | Context Menu not coming on the links | 2024-16 SPT
#567691 | UTUX: Template header shared component | 2024-20 SPT
#570475 | Last check, Download progress bug fix | 2024-20 SPT
#570523 | Create shared component for 'Update Item' | 2024-20 SPT
#573752 | Shared component for File Menu | 2024-20 SPT