## Sheet1
Entity Type | ID | Name | Effort | Team Sprint | Sprint Start | Sprint End | Start Date | End Date | Status | SpillOver | Sprint Goal | Comments
UserStory | 505975 | Fit to screen and zoom-in | 2 | 2024-07 SPT | 2024-04-04 | 2024-04-17 | 2024-04-10 14:07 | 2024-04-16 08:14 | Done | No | UTUX: Topology Planning
UserStory | 526604 | Create topology toolbar UI component | 3 | 2024-08 SPT | 2024-04-18 | 2024-05-01 | 2024-04-08 08:54 | 2024-04-22 10:10 | Done | No | UTUX : Toolbar+comments+context menu+patten generation for endpoints
UserStory | 530178 | Belden UI Core Components | 8 | 2024-09 SPT | 2024-05-02 | 2024-05-15 | 2024-04-25 11:30 | 2024-05-06 11:47 | Done | No
UserStory | 486522 | Context Menu- UI | 5 | 2024-10 SPT | 2024-05-16 | 2024-05-29 | 2024-04-24 07:08 | 2024-05-30 07:41 | Done | No | [UTUX] [PLNR] Topology planner to be completed
UserStory | 531011 | Zoom functionality - Dynamically update zoom level percentage based on yfiles | 3 | 2024-10 SPT | 2024-05-16 | 2024-05-29 | 2024-05-16 11:39 | 2024-05-21 13:10 | Done | No | [UTUX] [PLNR] Topology planner to be completed
UserStory | 543253 | PR review and Unit test cases Context Menu | 3 | 2024-11 SPT | 2024-05-17 | 2024-06-12 | 2024-06-03 08:09 | 2024-06-06 04:45 | Done | No | [UTUX]: Topology planning - Complete label/text related use-cases
UserStory | 486538 | background image for canvas | 3 | 2024-12 SPT | 2024-06-13 | 2024-06-26 | 2024-06-04 08:34 | 2024-06-21 08:33 | Done | Yes | [2024-12] [UTUX] Implement Topology Planning - Background Image & Comments
UserStory | 486519 | Edge labels | 3 | 2024-13 SPT | 2024-06-27 | 2024-07-10 | 2024-06-18 | 2024-07-01 08:34 | Done | No | [UTUX]: Topology planning - Complete label/text related use-cases
UserStory | 489972 | Implement Modal dialog for auto update | 5 | 2024-13 SPT | 2024-06-27 | 2024-07-10 | 2024-06-28 12:16 | 2024-07-05 08:05 | Done | No | [2024-13] [UTUX] Auto-update feature (Feature Flag & Modal)
UserStory | 551536 | Delete Edge Labels | 2 | 2024-13 SPT | 2024-06-27 | 2024-07-10 | 2024-07-08 09:52 | 2024-07-08 14:22 | Done | No | [UTUX]: Topology planning - Complete label/text related use-cases
Bug | 486528 | Bug Fix | 2 | 2024-14 SPT | 2024-07-11 | 2024-07-24 | 2024-07-18 06:27 | 2024-07-25 07:39 | Done | No | [2024-14] [UTUX] Topology planning (Unde Redo, Bug Fixes, & Manual Testing)
Bug | 552804 | Background Image Fix | 3 | 2024-14 SPT | 2024-07-11 | 2024-07-24 | 2024-07-08 11:44 | 2024-07-23 08:43 | Done | No | [2024-14] [UTUX] Topology planning (Unde Redo, Bug Fixes, & Manual Testing)
Bug | 559237 | UTUX: Bug Fix - Issues in Resizing | 1 | 2024-15 SPT | 2024-07-25 | 2024-08-07 | 2024-07-25 10:59 | 2024-07-26 07:01 | Done | No
UserStory | 489992 | Implement: Show the Last check date and time for the update. | 2 | 2024-15 SPT | 2024-07-25 | 2024-08-07 | 2024-07-31 07:12 | 2024-08-05 11:16 | Done | No | [2024-14] [UTUX] Implement Auto-update feature (check for new update, feature flag, feature list, remind me later, & skip)
UserStory | 559498 | UTUX:Implement automatic check on application start | 2 | 2024-15 SPT | 2024-07-25 | 2024-08-07 | 2024-07-30 08:34 | 2024-08-05 11:16 | Done | No
Bug | 559868 | Labels/Text on the Dialogs are not in sync with labels in design | 1 | 2024-16 SPT | 2024-08-08 | 2024-08-21 | 2024-08-07 09:52 | 2024-08-20 12:01 | Done | No
Bug | 559902 | Symbols for "Subnet" and "Template" are not as per the design | 1 | 2024-16 SPT | 2024-08-08 | 2024-08-21 | 2024-08-05 17:14 | 2024-08-20 11:59 | Done | No
Bug | 560435 | Device/Endpoint get the same name (Device 1/Endpoint 1) if user has drawn a topology pattern | 2 | 2024-16 SPT | 2024-08-08 | 2024-08-21 | 2024-08-07 10:16 | 2024-08-20 12:09 | Done | No
Bug | 560447 | Context Menu not coming on the links | 2 | 2024-16 SPT | 2024-08-08 | 2024-08-21 | 2024-08-06 07:41 | 2024-08-20 11:58 | Done | No
UserStory | 573839 | UTUX: Integrate Template Header component in monorepo | 2 | 2024-20 SPT | 2024-09-19 | 2024-10-16 | 2024-10-03 11:43 |  | In Progress | No
UserStory | 567691 | UTUX: Template header shared component | 3 | 2024-20 SPT | 2024-09-19 | 2024-10-16 | 2024-10-01 11:15 | 2024-10-03 11:42 | Done | No
Bug | 570475 | Last check, Download progress bug fix | 2 | 2024-20 SPT | 2024-09-19 | 2024-10-16 | 2024-09-16 11:35 | 2024-09-23 07:43 | Done | No | [UTUX] Implement Software auto update feature
UserStory | 570523 | Create shared component for 'Update Item' | 3 | 2024-20 SPT | 2024-09-19 | 2024-10-16 | 2024-09-30 07:58 | 2024-10-03 11:42 | Done | No
UserStory | 573752 | Shared component for File Menu | 3 | 2024-20 SPT | 2024-09-19 | 2024-10-16 | 2024-09-27 09:23 | 2024-10-03 11:42 | Done | No